## Product backlog
PRODUCT BACKLOG (Game: Survivor)
ID | Feature | Category | Priority | Sprint 1 | Sprint 2 | Sprint 3
0 | Display menu screen on program start | Menu | M | x
1 | Menu with "start game" and "exit" buttons | Menu | M | x
2 | Show the rules of the game when needed by user | Menu or Turn | M | x
3 | Screen to select the number of players | Init | M | x
4 | Display game board | Init | M | x
5 | Place all pawns on first tile | Init | M | x
6 | Display "exit" button | Init and Turn | M | x
7 | Possibility to select character | Init | M | x
8 | Display score cards | Turn | M | x
9 | Update and display life and condition points of characters | Turn | M | x
10 | Display which player is playing the current turn | Turn | M |  | x
11 | Current player can roll the dice and see the result | Turn | M |  | x
12 | Move the pawn of the player forward according to dice result | Turn | M |  | x
13 | Calculate the variables (lifepoints, conditions & damage) if a player lands on a special tile | Turn | M |  | x
14 | Change current player after the end of the turn | Turn | M |  | x
15 | Show win screen and display name of winner when there is only 1 player alive | End | M |  | x
16 | "Go back to menu" button is displayed in the win screen | End | S |  |  | x
17 | Current player can pause and resume the game | Turn | S |  |  | x
18 | Produce sound for throw of a dice / moving pawn / win screen / special actions | Turn | C |  | x
19 | Display dice throw / moving pawn with an animation | Turn | C |  |  | x
20 | Menu extended with "settings" button (for example, containing screen resolution, audio volume, …) | Menu | C |  |  | x
21 | Possibility to select also computer players | Init | C |  |  | x
22 | Computer player is able to play the game | Turn | C |  |  | x

## Sprint backlog 1
SPRINT 1 BACKLOG
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
0 | As a player I want to see a menu screen on start so that I can start the game. | M | 30m | - Find a proper menu texture | - Button displayed on menu - Clicks not on the button area have no effect on game start
1 | As a player I want to start the game from the menu, so that I can play it. | M | 10m | - When clicked on button, execute action - If clicked on start button, init game | - Button displayed on menu screen - Clicks not on the button area have no effect on game start - Clicks on the button area make the screen change (to init phase)
1 | As a player I want to quit the program from the menu, so that I can stop playing. | M | 10m | - When clicked on button, execute action - If clicked on exit button, quit program | - Button displayed on menu screen - Clicks not on the button area have no effect on quit program - Clicks on the button area make the program quit
2 | As a player I want to be able to see the rules when needed so that I know how to play the game. | M | 30m | - Find a proper button texture - Display rules only after the button has been clicked - Exit button to quit the rules overview and return to previous screen - Able to scroll through the rules overview in case that it does not fit the screen | - Button displayed on menu screen - Clicks not on the button area have no effect on quit program - Clicks on the button area will display the rules overview - Scrollable if the overview does not fit the screen
3 | As a Product owner I want the option to select the number of players so that the game can be played with multiple players. | M | 30m | - Load screen select number players - Display text "Choose how many players" - Add Dropdown menu with numbers (max 4 players) - Add Play/ Go button | - Dropdown menu displayed on the menu screen. - Text displayed on the menu screen - Player can select number of players with dropdown menu - Click on the button area starts the game with the selected number players
4 | As a player I want to see a game board so that I can play the game. | M | 2h | - Load and display the board game | - Starting the game - Show the image - Readable board
5 | As a player I want to see pawns in the game so that I know which pawn I am controlling | M | 1h | -Initialize the players on the start tile -Show which player turn it is | - Player pawn is displayed on the board - Player can see on score board which pawn he is controlling
6 | As a player I want to quit the program from the board so that I can stop playing. | M | 15m | -Quit pygame | - The quit button must close the pygame
7 | As a player I want to be able to select which character I'm going to play as | M | 45m | - Add dropdown menu with character names - Load and display score card of character | - Dropdown menu is displayed on the screen - Player can select character - Player can see score card of selected character
8 | As a player I want to be able to quickly see what the current score is | M | 20m | - Display scoreboard with the default statistics of each player | - The statistics of each player is displayed underneath the game board
9 | As a player I want to be able to see an updated version of the stats after each turn | M | 1h | - Calculate new stats - Update the scoreboard with the updated statistics of each player | - The statistics of each player is displayed underneath the game board

## Sprint backlog 2
SPRINT 2 BACKLOG
ID | User story | Priority | Time Estimation | Tasks | Acceptance criteria
10 | As a player I want to see whose turn it is so that I know who is playing now. | M | 25m | - Determine who current player is - Define area to show this information - Display player's name/number | - The current player name/number is visible for the other players
11 | As a player I want to be able to roll and see the result of the die throw so that I know how many steps I need to take. | M | 1h | - Define area where die throws are shown - Load and display button in defined area - Show the result of the die throw in defined area - When clicked on the button, update the result of the die throw | - Click on the button area, updates the result of the die throw - The result of the die throw in the defined area is visible for all players
12 | As a player I want the pawn move forward according to my throw so that I can see where I am standing now. | M | 1h | - Update current position of the player pawn to the new position - Display the new position of the player on the screen | - Player pawn is moved forward according to the result of the die throw - All the players are able to see the new position of the player pawn
13 | As a product owner I want special actions in the game so that the game is more challenging and fun to play. | M | 3h | - Connect specific tiles with an event - Display screen with event notification - Show player's name/number that activated the event in screen | - An event will be triggered when a player steps on a tile area that is connected to an event. - A screen is displayed with what event is occuring - The player's name/number is displayed in the screen
14 | As a product owner I want the player's turn end so that a different player can play. | M | 30m | - Display next player's name/number in defined area at the end of current player's turn | - The name/number of the new player is displayed in the defined area
15 | As a player I want to see a win screen so that I know who won the game. | M | 30m | - Define area where winning screen is shown - Load and display screen with the name/number of the player that won in the defined area - Display winning text | - All players sees a screen with the name/number of the player that won
18 | As a user I want certain game elements to have a sound corresponding to their function. | C | 45m | - Decide on sounds to use for certain functions of the game - Load sounds and make them capable of playing | - Hearing playing the sound - Correct sound playing by the right scenario